## dozer
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Dozer Productivity Data Records
Form - 1
[10 empty] | Blade Measurement | [6 empty] | Delay
Date: | Project Code: | Data Collector | Number of Equipment Types: | Dozer Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Dozer Blade Type (S, U, SU, C) | Task Type | Description | Soil Type | H | W | L | Unit | Blad Load (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
2017-03-10 | 1 | Geitahun Tesfaye | 1 | 1 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 142 | 63.2789
|  |  |  | 2 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 65 | 138.24 |  | 2.496 | 106.9714
|  |  |  | 3 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 134 | 67.0567
|  |  |  | 4 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 76 | 118.2316
|  |  |  | 5 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 64 | 140.4
|  |  |  | 6 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 67 | 134.1134
|  |  |  | 7 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 58 | 154.9241
|  |  |  | 8 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 72 | 124.8
|  |  |  | 9 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 41 | 219.161
|  |  |  | 10 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 48 | 187.2
|  |  |  | 11 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 73 | 123.0904
|  |  |  | 12 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 64 | 140.4
|  |  |  | 13 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 68 | 132.1412
|  |  |  | 14 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 44 | 204.2182
|  |  |  | 15 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 56 | 160.4571
|  |  |  | 16 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 54 | 166.4
|  |  |  | 17 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 61 | 147.3049
|  |  |  | 18 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 78 | 115.2
|  |  |  | 19 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 69 | 130.2261
|  |  |  | 20 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 77 | 116.6961
|  |  |  | 21 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 73 | 123.0904
|  |  |  | 22 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 233 | 38.5648 |  | 161
|  |  |  | 23 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 41 | 219.161
|  |  |  | 24 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 63 | 142.6286
|  |  |  | 25 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 66 | 136.1455
|  |  |  | 26 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 52 | 172.8
|  |  |  | 27 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 74 | 121.427
|  |  |  | 28 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 35 | 256.7314
|  |  |  | 29 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 44 | 204.2182
|  |  |  | 30 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 76 | 118.2316
|  |  |  | 31 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 45 | 199.68
|  |  |  | 32 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 69 | 130.2261
|  |  |  | 33 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 47 | 191.183
|  |  |  | 34 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 51 | 176.1882
|  |  |  | 35 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 38 | 236.4632
|  |  |  | 36 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 42 | 213.9429
|  |  |  | 37 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 71 | 126.5577
|  |  |  | 38 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 66 | 136.1455
|  |  |  | 39 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 6780 | 1.3253 |  | 6713
|  |  |  | 40 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 234 | 38.4
|  |  |  | 41 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 56 | 160.4571
|  |  |  | 42 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 75 | 119.808
|  |  |  | 43 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 62 | 144.929
|  |  |  | 44 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 79 | 113.7418
|  |  |  | 45 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 71 | 126.5577
|  |  |  | 46 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 60 | 149.76
|  |  |  | 47 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 64 | 140.4
|  |  |  | 48 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 67 | 134.1134
|  |  |  | 49 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 69 | 130.2261
|  |  |  | 50 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 55 | 163.3745
|  |  |  | 51 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 78 | 115.2
|  |  |  | 52 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 64 | 140.4
|  |  |  | 53 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 82 | 109.5805
|  |  |  | 54 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 44 | 204.2182
|  |  |  | 55 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 57 | 157.6421
|  |  |  | 56 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 63 | 142.6286
|  |  |  | 57 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 61 | 147.3049
|  |  |  | 58 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 70 | 128.3657
|  |  |  | 59 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 73 | 123.0904
|  |  |  | 60 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 67 | 134.1134
|  |  |  | 61 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 51 | 176.1882
|  |  |  | 62 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 72 | 124.8
|  |  |  | 63 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 64 | 140.4
|  |  |  | 64 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 70 | 128.3657
|  |  |  | 65 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 473 | 18.997 |  | 402
|  |  |  | 66 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 56 | 160.4571
|  |  |  | 67 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 84 | 106.9714
|  |  |  | 68 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 93 | 96.6194
|  |  |  | 69 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 77 | 116.6961
|  |  |  | 70 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 81 | 110.9333
|  |  |  | 71 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 90 | 99.84
|  |  |  | 72 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 83 | 108.2602
|  |  |  | 73 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 88 | 102.1091
|  |  |  | 74 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 79 | 113.7418
|  |  |  | 75 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 47 | 191.183
|  |  |  | 76 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 87 | 103.2828
|  |  |  | 77 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 66 | 136.1455
|  |  |  | 78 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 75 | 119.808
|  |  |  | 79 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 83 | 108.2602
|  |  |  | 80 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 94 | 95.5915
|  |  |  | 81 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 82 | 109.5805
|  |  |  | 82 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 391 | 22.9811 |  |  | 295
|  |  |  | 83 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 46 | 195.3391
|  |  |  | 84 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 55 | 163.3745
|  |  |  | 85 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 71 | 126.5577
|  |  |  | 86 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 79 | 113.7418
|  |  |  | 87 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 85 | 105.7129
|  |  |  | 88 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 83 | 108.2602
|  |  |  | 89 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 94 | 95.5915
|  |  |  | 90 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 76 | 118.2316
|  |  |  | 91 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 64 | 140.4
|  |  |  | 92 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 76 | 118.2316
|  |  |  | 93 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 97 | 92.6351
|  |  |  | 94 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 48 | 187.2
|  |  |  | 95 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 76 | 118.2316
|  |  |  | 96 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 75 | 119.808
|  |  |  | 97 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 82 | 109.5805
|  |  |  | 98 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 80 | 112.32
|  |  |  | 99 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 91 | 98.7429
|  |  |  | 100 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 88 | 102.1091
|  |  |  | 101 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 67 | 134.1134
|  |  |  | 102 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 82 | 109.5805
|  |  |  | 103 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 87 | 103.2828
|  |  |  | 104 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 62 | 144.929
|  |  |  | 105 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 94 | 95.5915
|  |  |  | 106 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 93 | 96.6194
|  |  |  | 107 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 96 | 93.6
|  |  |  | 108 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 451 | 19.9237 |  | 359
|  |  |  | 109 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 87 | 103.2828
|  |  |  | 110 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 89 | 100.9618
|  |  |  | 111 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 77 | 116.6961
|  |  |  | 112 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 86 | 104.4837
|  |  |  | 113 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 95 | 94.5853
|  |  |  | 114 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 92 | 97.6696
|  |  |  | 115 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 97 | 92.6351
|  |  |  | 116 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 84 | 106.9714
|  |  |  | 117 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 90 | 99.84
|  |  |  | 118 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 86 | 104.4837
|  |  |  | 119 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 342 | 26.2737 |  | 291
|  |  |  | 120 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 93 | 96.6194
|  |  |  | 121 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 91 | 98.7429
|  |  |  | 122 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 156 | 57.6 |  |  | 74
|  |  |  | 123 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 87 | 103.2828
|  |  |  | 124 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 48 | 187.2
|  |  |  | 125 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 90 | 99.84
|  |  |  | 126 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 93 | 96.6194
|  |  |  | 127 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 67 | 134.1134
|  |  |  | 128 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 83 | 108.2602
|  |  |  | 129 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 76 | 118.2316
|  |  |  | 130 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 84 | 106.9714
|  |  |  | 131 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 81 | 110.9333
|  |  |  | 132 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 97 | 92.6351
|  |  |  | 133 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 86 | 104.4837
|  |  |  | 134 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 58 | 154.9241
|  |  |  | 135 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 74 | 121.427
|  |  |  | 136 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 92 | 97.6696
|  |  |  | 137 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 44 | 204.2182
|  |  |  | 138 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 93 | 96.6194
|  |  |  | 139 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 84 | 106.9714
|  |  |  | 140 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 86 | 104.4837
|  |  |  | 141 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 59 | 152.2983
|  |  |  | 142 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 72 | 124.8
|  |  |  | 143 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 84 | 106.9714
|  |  |  | 144 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 92 | 97.6696
|  |  |  | 145 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 91 | 98.7429
|  |  |  | 146 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 70 | 128.3657
|  |  |  | 147 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 56 | 160.4571
|  |  |  | 148 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 92 | 97.6696
|  |  |  | 149 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 84 | 106.9714
|  |  |  | 150 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 88 | 102.1091
|  |  |  | 151 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 82 | 109.5805
|  |  |  | 152 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 94 | 95.5915
|  |  |  | 153 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 142 | 63.2789 |  | 58
|  |  |  | 154 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 87 | 103.2828
|  |  |  | 155 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 98 | 91.6898
|  |  |  | 156 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 88 | 102.1091
|  |  |  | 157 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 103 | 87.2388
|  |  |  | 158 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 96 | 93.6
|  |  |  | 159 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 72 | 124.8
|  |  |  | 160 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 109 | 82.4367
|  |  |  | 161 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 113 | 79.5186
|  |  |  | 162 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 81 | 110.9333
|  |  |  | 163 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 84 | 106.9714
|  |  |  | 164 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 115 | 78.1357
|  |  |  | 165 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 63 | 142.6286
|  |  |  | 166 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 84 | 106.9714
|  |  |  | 167 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 96 | 93.6
|  |  |  | 168 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 105 | 85.5771
|  |  |  | 169 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 88 | 102.1091
|  |  |  | 170 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 109 | 82.4367
|  |  |  | 171 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 85 | 105.7129
|  |  |  | 172 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 87 | 103.2828
|  |  |  | 173 | 1F,1OP,1H | SU | 01-Earth | Clearing and graping using Dozer | clay | 1.3 | 0.6 | 3.2 | m | 2.496 | 96 | 93.6
|  |  |  | Average | [5 empty] | 1.3 | 0.6 | 3.2 |  | 2.496 | 125.1337 | 121.3667

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
2017-03-10 | 1 | Geitahun Tesfaye | sec | Clearing and graping using Dozer | Dozer | 1 | 142
[6 empty] | 2 | 65
[6 empty] | 3 | 134
[6 empty] | 4 | 76
[6 empty] | 5 | 64
[6 empty] | 6 | 67
[6 empty] | 7 | 58
[6 empty] | 8 | 72
[6 empty] | 9 | 41
[6 empty] | 10 | 48
[6 empty] | 11 | 73
[6 empty] | 12 | 64
[6 empty] | 13 | 68
[6 empty] | 14 | 44
[6 empty] | 15 | 56
[6 empty] | 16 | 54
[6 empty] | 17 | 61
[6 empty] | 18 | 78
[6 empty] | 19 | 69
[6 empty] | 20 | 77
[6 empty] | 21 | 73
[6 empty] | 22 | 233 |  | 161
[6 empty] | 23 | 41
[6 empty] | 24 | 63
[6 empty] | 25 | 66
[6 empty] | 26 | 52
[6 empty] | 27 | 74
[6 empty] | 28 | 35
[6 empty] | 29 | 44
[6 empty] | 30 | 76
[6 empty] | 31 | 45
[6 empty] | 32 | 69
[6 empty] | 33 | 47
[6 empty] | 34 | 51
[6 empty] | 35 | 38
[6 empty] | 36 | 42
[6 empty] | 37 | 71
[6 empty] | 38 | 66
[6 empty] | 39 | 6780 |  | 6713
[6 empty] | 40 | 234
[6 empty] | 41 | 56
[6 empty] | 42 | 75
[6 empty] | 43 | 62
[6 empty] | 44 | 79
[6 empty] | 45 | 71
[6 empty] | 46 | 60
[6 empty] | 47 | 64
[6 empty] | 48 | 67
[6 empty] | 49 | 69
[6 empty] | 50 | 55
[6 empty] | 51 | 78
[6 empty] | 52 | 64
[6 empty] | 53 | 82
[6 empty] | 54 | 44
[6 empty] | 55 | 57
[6 empty] | 56 | 63
[6 empty] | 57 | 61
[6 empty] | 58 | 70
[6 empty] | 59 | 73
[6 empty] | 60 | 67
[6 empty] | 61 | 51
[6 empty] | 62 | 72
[6 empty] | 63 | 64
[6 empty] | 64 | 70
[6 empty] | 65 | 473 |  | 402
[6 empty] | 66 | 56
[6 empty] | 67 | 84
[6 empty] | 68 | 93
[6 empty] | 69 | 77
[6 empty] | 70 | 81
[6 empty] | 71 | 90
[6 empty] | 72 | 83
[6 empty] | 73 | 88
[6 empty] | 74 | 79
[6 empty] | 75 | 47
[6 empty] | 76 | 87
[6 empty] | 77 | 66
[6 empty] | 78 | 75
[6 empty] | 79 | 83
[6 empty] | 80 | 94
[6 empty] | 81 | 82
[6 empty] | 82 | 391 |  |  | 295
[6 empty] | 83 | 46
[6 empty] | 84 | 55
[6 empty] | 85 | 71
[6 empty] | 86 | 79
[6 empty] | 87 | 85
[6 empty] | 88 | 83
[6 empty] | 89 | 94
[6 empty] | 90 | 76
[6 empty] | 91 | 64
[6 empty] | 92 | 76
[6 empty] | 93 | 97
[6 empty] | 94 | 48
[6 empty] | 95 | 76
[6 empty] | 96 | 75
[6 empty] | 97 | 82
[6 empty] | 98 | 80
[6 empty] | 99 | 91
[6 empty] | 100 | 88
[6 empty] | 101 | 67
[6 empty] | 102 | 82
[6 empty] | 103 | 87
[6 empty] | 104 | 62
[6 empty] | 105 | 94
[6 empty] | 106 | 93
[6 empty] | 107 | 96
[6 empty] | 108 | 451 |  | 359
[6 empty] | 109 | 87
[6 empty] | 110 | 89
[6 empty] | 111 | 77
[6 empty] | 112 | 86
[6 empty] | 113 | 95
[6 empty] | 114 | 92
[6 empty] | 115 | 97
[6 empty] | 116 | 84
[6 empty] | 117 | 90
[6 empty] | 118 | 86
[6 empty] | 119 | 342 |  | 291
[6 empty] | 120 | 93
[6 empty] | 121 | 91
[6 empty] | 122 | 156 |  |  | 74
[6 empty] | 123 | 87
[6 empty] | 124 | 48
[6 empty] | 125 | 90
[6 empty] | 126 | 93
[6 empty] | 127 | 67
[6 empty] | 128 | 83
[6 empty] | 129 | 76
[6 empty] | 130 | 84
[6 empty] | 131 | 81
[6 empty] | 132 | 97
[6 empty] | 133 | 86
[6 empty] | 134 | 58
[6 empty] | 135 | 74
[6 empty] | 136 | 92
[6 empty] | 137 | 44
[6 empty] | 138 | 93
[6 empty] | 139 | 84
[6 empty] | 140 | 86
[6 empty] | 141 | 59
[6 empty] | 142 | 72
[6 empty] | 143 | 84
[6 empty] | 144 | 92
[6 empty] | 145 | 91
[6 empty] | 146 | 70
[6 empty] | 147 | 56
[6 empty] | 148 | 92
[6 empty] | 149 | 84
[6 empty] | 150 | 88
[6 empty] | 151 | 82
[6 empty] | 152 | 94
[6 empty] | 153 | 142 |  | 58
[6 empty] | 154 | 87
[6 empty] | 155 | 98
[6 empty] | 156 | 88
[6 empty] | 157 | 103
[6 empty] | 158 | 96
[6 empty] | 159 | 72
[6 empty] | 160 | 109
[6 empty] | 161 | 113
[6 empty] | 162 | 81
[6 empty] | 163 | 84
[6 empty] | 164 | 115
[6 empty] | 165 | 63
[6 empty] | 166 | 84
[6 empty] | 167 | 96
[6 empty] | 168 | 105
[6 empty] | 169 | 88
[6 empty] | 170 | 109
[6 empty] | 171 | 85
[6 empty] | 172 | 87
[6 empty] | 173 | 96
[6 empty] | Count (a) | 173 | 0 | 6 | 2 | 0 | 0 | 0
[6 empty] | Total (b) | 21665 | 0 | 7984 | 369 | 0 | 0 | 0
[6 empty] | Average (b/a) | 125.2312 | 0 | 1330.6667 | 184.5 | 0 | 0 | 0

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE |  |  |  |  | Project Code | 1
Form - 6 - Daily Input Variables |  |  |  |  | Task/particular | 01-Earth/ | Clearing and graping using Dozer
[5 empty] | Data Collector | Geitahun Tesfaye
[5 empty] | Data count | 1 | 2 | 3 | 5
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description | 2017-03-10
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | Range (1 - 20) | Vaules for each of the crews understudy | 3
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | Range og each category (0 - 10) | Vaules for each of the crews understudy | 1F, 1Op, 1Helper
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size | 4
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks. | 0
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision | 4
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80% | 4
| 1.8 | Willingness to perform other's tasks | Categorical |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing | 4
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University | 3
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | Range (0 - 150) |  | 0
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | Range (0 - 1000) |  | 0
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | Range (0 - 40) |  | 9
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | Range (1 - 5) |  | 1
| 1.14 | Job security | Integer (Average length of unemployment period, months) | Range (0 -12) | Average per crew member. | 0
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | Range (0 - 10) | Work of equipment (crane, forklift) | 0
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | Range (0 - 60) |  | 0
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | Range (0 - 10) | Transport equipment (man lift) | 0
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | Range (0 - 60) |  | 0
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | Range (1 - 20) |  | 1
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | Range (0 - 30) |  | 0
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | Range (0 - 30) |  | 0
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | Range (0 -100) |  | 100
| 3.7 | Use of overtime | Real number (Average over time per week) | Range (0 -38) | Over all project activities (besides the one under study). | 0

## productivity
Construction Management Institute (CMI) with Bahir Dar Institute of Technology (BiT)
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Equipment Productivity Data Instance Sheet
| Task/Activity/Particular: |  | Dam, Divi-1 (MATERIAL DEVELOPMENT ), Earth-Excavation using Hydraulic Excavator
Equipment:
MPDM
Data Count | Data Collector | Date | Project Code | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Productivity (m3/hr) | Avg. Cycle Time (Seconds) | Environment | Equipment | Labor | Material | Management | Others